## GanttChart
A.G. Group
Gannt Chart for Job Winner Application
Grace Kim
Objectives |  | 2015 |  |  | 2015 |  |  | 2016 |  |  | 2016
A | Specific Aims | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June
1 | AIM 1: Research
1.1 | market survey
1.2 | user survey
1.3 | IT survey
1.4 | platform strategy analysis
1.5 | benchmarking
2 | AIM 2: Strategy Development
2.1 | establishing profit strategy
2.2 | marketing strategy
3 | AIM 3:Preparation for App Development
3.1 | organizing development team
3.2 | enrollment of new developers(company+staff)
3.3 | registering EIN(Employer Identification Number)
4 | AIM 4: Planning
4.1 | app concept
4.2 | defining functions app and systemizing
4.3 | making a flow map
4.4 | making a wireframe
4.5 | produce a prototype(paper, ppt)
4.6 | prototype user test
5 | AIM 5: Design
5.1 | Design specifications
5.2 | Design guidelines
5.3 | Concept Design
5.4 | Style Guide
5.5 | GUI Design(Graphic User Interface)
5.6 | Content Design
6 | AIM 6: Development
6.1 | Development Specifications
6.2 | Function Development
6.3 | UI(User Interface) Development
6.4 | Debug & optimization
7 | AIM 7: Preview
7.1 | Prototype test
8 | AIM 8: Inspection before Launch
8.1 | completing beta version & inner assessment
8.2 | beta version user test
8.3 | user test feedback analysis
8.4 | error correction & optimization
B | Marketing & Sales Strategy
1 | Promotion
2 | Opening customer service website
3 | Advertising
C | Launch&Follow-up Management
1 | Summit app store & examination standard
2 | Launch
3 | gather users' feedback
4 | assessment and planning update
5 | update
D | Follow on Funding Plan
1 | Business Plan Development
2 | Apply for additional loans
3 | Engage Commercial partners(JobKorea)
Completed
Projected